## Sheet1
Simple project plan to develop new product in a region of England and distribute it via the travel trade
Workstream | Activities | [12 empty] | Milestones | Date
|  | J | F | M | A | M | J | J | A | S | O | N | D
Workstream 1: e.g. research | Activity 1: e.g. focus groups x2 | [12 empty] | Results collated and reported | bar: J to F
Activity 2: e.g. desk research | bar: J to F
Activity 3: e.g. product testing | bar: M
Workstream 2: e.g product development | Activity 1: e.g. product audit | [12 empty] | 4 itineraries described and designed | bar: F to M
Activity 2: e.g. itinerary planning | bar: M to A
Workstream 3: e.g. trade engagement | Activity 1: e.g. trade event 1 | [12 empty] | Engagement activity completed | bar: S
Activity 2: e.g. trade event 2 (international) | bar: O
Activity 3: e.g. familiarisation visit 1 | bar: N
Activity 4: e.g. familiarisation visit 2 | bar: N
Activity 4: e.g. hosted dinner | bar: N
Activity 5: e.g. trade engagement materials | bar: J to A
Workstream 4: management | Activity 1: e.g. communications | [12 empty] | Evaluation report delivered. Final claim made | bar: M; J; S; D
Activity 2: e.g. monitoring activity including surveys | bar: O to D
Activity 3: e.g. management/delivery
Activity 6: evaluation, interim and final report | bar: J; D
NB: for shorter projects a weekly or even daily timetable may be advantageous.